## Modules
Modules
Organization and Company setup
1. Organization setup.
2. Company setup.
Employee/User setup
User Group setup
User Roles setup
Discipline set up
Vendor Setup
Category setup
Category setup contains Client, Project, Phase, Activity, Fee Type and Fee Schedule.
1. Client setup module
2. Project setup module
3. Phase setup module
4. Activity setup module
5. Fee type setup module
6. Fee schedule setup module
Item cost setup
1. Disbursement setup
2. Service setup.
3. Material setup.
4. Expense set up.
TaskManagement
TicketManagement
Common Utilities
1. Document attachemnt.
2. Document upload
Dashboard
Design Style sheets
Reports
History of Updates
Jquery function for Validation

## ModuleBudgetedWork
Modules | Sub-Modules | BudgetedTask | Bud.Days | Activity | Days | User | 27 | 0
Organization |  | Create Table into DB. | 1 |  |  | Arif E | Modules | Total Budget Days | Time | Total | Resource
Organization |  | Create repository for Add. | 0 | [6 empty] | 27
Organization |  | Create repository for Delete. | 0 |  |  |  | Organization | 2 | 0 | 0 | Arif E
Organization |  | Create repository for Update. | 0 |  |  |  | Company | 4 | 0 |  | Surbhi B
Organization |  | Create actions in web API for Add. | 0 |  |  |  | Employee/User | 4 | 0 |  | Manoj P
Organization |  | Create actions in web API for Delete. | 0 |  |  |  | User Group | 3 | 0 |  | Pankaj S
Organization |  | Create actions in web API for Update. | 0 |  |  |  | User Roles | 3 | 0
Organization |  | Mapping of DataModel into Business Entity. | 0 |  |  |  | Discipline | 4 | 0
Organization |  | Business service Add. | 0 |  |  |  | Vendor | 4 | 0
Organization |  | Business service Delete. | 0 |  |  |  | Category-Client | 3 | 0
Organization |  | Business service Update. | 0 |  |  |  | Category-Project
Organization |  | Create View. | 1 |  |  |  | Category-Phase
Organization |  | Create client side and server side validation. | 0 |  |  |  | Category-Activity
Organization |  | Cosume Rest API for Add. | 0 |  |  |  | Category-FeeType
Organization |  | Cosume Rest API for Update. | 0 |  |  |  | Category-FeeSchedule
Organization |  | Cosume Rest API for Delete. | 0 |  |  |  | Itemcost-Disbursement
Itemcost-Expense
Itemcost-Material
|  | Total Days. | 2 |  | 0 |  | Itemcost-Service
Task Management
Company |  | Create Table into DB. | 2 |  |  |  | TicketManagement
Company |  | Create repository for Add. | 0 |  |  |  | Dashboard
Company |  | Create repository for Delete. | 0 |  |  |  | Design Style sheets
Company |  | Create repository for Update. | 0 |  |  |  | Reports
Company |  | Create actions in web API for Add. | 0 |  |  |  | History of Updates
Company |  | Create actions in web API for Delete. | 0 |  |  |  | Jquery function for val
Company |  | Create actions in web API for Update. | 0
Company |  | Mapping of DataModel into Business Entity. | 0
Company |  | Business service Add. | 0
Company |  | Business service Delete. | 0
Company |  | Business service Update. | 0
Company |  | Create View. | 2
Company |  | Create client side and server side validation. | 0
Company |  | Cosume Rest API for Add. | 0
Company |  | Cosume Rest API for Update. | 0
Company |  | Cosume Rest API for Delete. | 0
|  | Total Days. | 4 |  | 0
Employee/User |  | Create Table into DB. | 2
Employee/User |  | Create repository for Add.
Employee/User |  | Create repository for Delete.
Employee/User |  | Create repository for Update.
Employee/User |  | Create actions in web API for Add.
Employee/User |  | Create actions in web API for Delete.
Employee/User |  | Create actions in web API for Update.
Employee/User |  | Mapping of DataModel into Business Entity.
Employee/User |  | Business service Add.
Employee/User |  | Business service Delete.
Employee/User |  | Business service Update.
Employee/User |  | Create View. | 2
Employee/User |  | Create client side and server side validation.
Employee/User |  | Cosume Rest API for Add.
Employee/User |  | Cosume Rest API for Update.
Employee/User |  | Cosume Rest API for Delete.
|  | Total Days. | 4 |  | 0
User Group |  | Create Table into DB. | 2
User Group |  | Create repository for Add.
User Group |  | Create repository for Delete.
User Group |  | Create repository for Update.
User Group |  | Create actions in web API for Add.
User Group |  | Create actions in web API for Delete.
User Group |  | Create actions in web API for Update.
User Group |  | Mapping of DataModel into Business Entity.
User Group |  | Business service Add.
User Group |  | Business service Delete.
User Group |  | Business service Update.
User Group |  | Create View. | 1
User Group |  | Create client side and server side validation.
User Group |  | Cosume Rest API for Add.
User Group |  | Cosume Rest API for Update.
User Group |  | Cosume Rest API for Delete.
|  | Total Days. | 3 |  | 0
User Roles |  | Create Table into DB. | 2
User Roles |  | Create repository for Add.
User Roles |  | Create repository for Delete.
User Roles |  | Create repository for Update.
User Roles |  | Create actions in web API for Add.
User Roles |  | Create actions in web API for Delete.
User Roles |  | Create actions in web API for Update.
User Roles |  | Mapping of DataModel into Business Entity.
User Roles |  | Business service Add.
User Roles |  | Business service Delete.
User Roles |  | Business service Update.
User Roles |  | Create View. | 1
User Roles |  | Create client side and server side validation.
User Roles |  | Cosume Rest API for Add.
User Roles |  | Cosume Rest API for Update.
User Roles |  | Cosume Rest API for Delete.
|  | Total Days. | 3 |  | 0
Discipline |  | Create Table into DB. | 2
Discipline |  | Create repository for Add.
Discipline |  | Create repository for Delete.
Discipline |  | Create repository for Update.
Discipline |  | Create actions in web API for Add.
Discipline |  | Create actions in web API for Delete.
Discipline |  | Create actions in web API for Update.
Discipline |  | Mapping of DataModel into Business Entity.
Discipline |  | Business service Add.
Discipline |  | Business service Delete.
Discipline |  | Business service Update.
Discipline |  | Create View. | 2
Discipline |  | Create client side and server side validation.
Discipline |  | Cosume Rest API for Add.
Discipline |  | Cosume Rest API for Update.
Discipline |  | Cosume Rest API for Delete.
|  | Total Days. | 4 |  | 0
Vendor |  | Create Table into DB. | 2
Vendor |  | Create repository for Add.
Vendor |  | Create repository for Delete.
Vendor |  | Create repository for Update.
Vendor |  | Create actions in web API for Add.
Vendor |  | Create actions in web API for Delete.
Vendor |  | Create actions in web API for Update.
Vendor |  | Mapping of DataModel into Business Entity.
Vendor |  | Business service Add.
Vendor |  | Business service Delete.
Vendor |  | Business service Update.
Vendor |  | Create View. | 2
Vendor |  | Create client side and server side validation.
Vendor |  | Cosume Rest API for Add.
Vendor |  | Cosume Rest API for Update.
Vendor |  | Cosume Rest API for Delete.
|  | Total Days. | 4 |  | 0
Category-Client |  | Create Table into DB. | 2
Category-Client |  | Create repository for Add.
Category-Client |  | Create repository for Delete.
Category-Client |  | Create repository for Update.
Category-Client |  | Create actions in web API for Add.
Category-Client |  | Create actions in web API for Delete.
Category-Client |  | Create actions in web API for Update.
Category-Client |  | Mapping of DataModel into Business Entity.
Category-Client |  | Business service Add.
Category-Client |  | Business service Delete.
Category-Client |  | Business service Update.
Category-Client |  | Create View. | 1
Category-Client |  | Create client side and server side validation.
Category-Client |  | Cosume Rest API for Add.
Category-Client |  | Cosume Rest API for Update.
Category-Client |  | Cosume Rest API for Delete.
|  | Total Days. | 3 |  | 0
Category-Project |  | Create Table into DB. | 1
Category-Project |  | Create repository for Add.
Category-Project |  | Create repository for Delete.
Category-Project |  | Create repository for Update.
Category-Project |  | Create actions in web API for Add.
Category-Project |  | Create actions in web API for Delete.
Category-Project |  | Create actions in web API for Update.
Category-Project |  | Mapping of DataModel into Business Entity.
Category-Project |  | Business service Add.
Category-Project |  | Business service Delete.
Category-Project |  | Business service Update.
Category-Project |  | Create View. | 1
Category-Project |  | Create client side and server side validation.
Category-Project |  | Cosume Rest API for Add.
Category-Project |  | Cosume Rest API for Update.
Category-Project |  | Cosume Rest API for Delete.
|  | Total Days. | 2 |  | 0
Category-Phase |  | Create Table into DB. | 1
Category-Phase |  | Create repository for Add.
Category-Phase |  | Create repository for Delete.
Category-Phase |  | Create repository for Update.
Category-Phase |  | Create actions in web API for Add.
Category-Phase |  | Create actions in web API for Delete.
Category-Phase |  | Create actions in web API for Update.
Category-Phase |  | Mapping of DataModel into Business Entity.
Category-Phase |  | Business service Add.
Category-Phase |  | Business service Delete.
Category-Phase |  | Business service Update.
Category-Phase |  | Create View. | 1
Category-Phase |  | Create client side and server side validation.
Category-Phase |  | Cosume Rest API for Add.
Category-Phase |  | Cosume Rest API for Update.
Category-Phase |  | Cosume Rest API for Delete.
|  | Total Days. | 2 |  | 0
Category-Activity |  | Create Table into DB. | 1
Category-Activity |  | Create repository for Add.
Category-Activity |  | Create repository for Delete.
Category-Activity |  | Create repository for Update.
Category-Activity |  | Create actions in web API for Add.
Category-Activity |  | Create actions in web API for Delete.
Category-Activity |  | Create actions in web API for Update.
Category-Activity |  | Mapping of DataModel into Business Entity.
Category-Activity |  | Business service Add.
Category-Activity |  | Business service Delete.
Category-Activity |  | Business service Update.
Category-Activity |  | Create View. | 1
Category-Activity |  | Create client side and server side validation.
Category-Activity |  | Cosume Rest API for Add.
Category-Activity |  | Cosume Rest API for Update.
Category-Activity |  | Cosume Rest API for Delete.
|  | Total Days. | 2 |  | 0
Category-FeeType |  | Create Table into DB. | 1
Category-FeeType |  | Create repository for Add.
Category-FeeType |  | Create repository for Delete.
Category-FeeType |  | Create repository for Update.
Category-FeeType |  | Create actions in web API for Add.
Category-FeeType |  | Create actions in web API for Delete.
Category-FeeType |  | Create actions in web API for Update.
Category-FeeType |  | Mapping of DataModel into Business Entity.
Category-FeeType |  | Business service Add.
Category-FeeType |  | Business service Delete.
Category-FeeType |  | Business service Update.
Category-FeeType |  | Create View. | 1
Category-FeeType |  | Create client side and server side validation.
Category-FeeType |  | Cosume Rest API for Add.
Category-FeeType |  | Cosume Rest API for Update.
Category-FeeType |  | Cosume Rest API for Delete.
|  | Total Days. | 2 |  | 0
Category-FeeSchedule |  | Create Table into DB. | 1
Category-FeeSchedule |  | Create repository for Add.
Category-FeeSchedule |  | Create repository for Delete.
Category-FeeSchedule |  | Create repository for Update.
Category-FeeSchedule |  | Create actions in web API for Add.
Category-FeeSchedule |  | Create actions in web API for Delete.
Category-FeeSchedule |  | Create actions in web API for Update.
Category-FeeSchedule |  | Mapping of DataModel into Business Entity.
Category-FeeSchedule |  | Business service Add.
Category-FeeSchedule |  | Business service Delete.
Category-FeeSchedule |  | Business service Update.
Category-FeeSchedule |  | Create View. | 1
Category-FeeSchedule |  | Create client side and server side validation.
Category-FeeSchedule |  | Cosume Rest API for Add.
Category-FeeSchedule |  | Cosume Rest API for Update.
Category-FeeSchedule |  | Cosume Rest API for Delete.
|  | Total Days. | 2 |  | 0
Itemcost-Disbursement |  | Create Table into DB. | 1
Itemcost-Disbursement |  | Create repository for Add.
Itemcost-Disbursement |  | Create repository for Delete.
Itemcost-Disbursement |  | Create repository for Update.
Itemcost-Disbursement |  | Create actions in web API for Add.
Itemcost-Disbursement |  | Create actions in web API for Delete.
Itemcost-Disbursement |  | Create actions in web API for Update.
Itemcost-Disbursement |  | Mapping of DataModel into Business Entity.
Itemcost-Disbursement |  | Business service Add.
Itemcost-Disbursement |  | Business service Delete.
Itemcost-Disbursement |  | Business service Update.
Itemcost-Disbursement |  | Create View. | 1
Itemcost-Disbursement |  | Create client side and server side validation.
Itemcost-Disbursement |  | Cosume Rest API for Add.
Itemcost-Disbursement |  | Cosume Rest API for Update.
Itemcost-Disbursement |  | Cosume Rest API for Delete.
|  | Total Days. | 2 |  | 0
Itemcost-Expense |  | Create Table into DB. | 1
Itemcost-Expense |  | Create repository for Add.
Itemcost-Expense |  | Create repository for Delete.
Itemcost-Expense |  | Create repository for Update.
Itemcost-Expense |  | Create actions in web API for Add.
Itemcost-Expense |  | Create actions in web API for Delete.
Itemcost-Expense |  | Create actions in web API for Update.
Itemcost-Expense |  | Mapping of DataModel into Business Entity.
Itemcost-Expense |  | Business service Add.
Itemcost-Expense |  | Business service Delete.
Itemcost-Expense |  | Business service Update.
Itemcost-Expense |  | Create View. | 1
Itemcost-Expense |  | Create client side and server side validation.
Itemcost-Expense |  | Cosume Rest API for Add.
Itemcost-Expense |  | Cosume Rest API for Update.
Itemcost-Expense |  | Cosume Rest API for Delete.
|  | Total Days. | 2 |  | 0
Itemcost-Material |  | Create Table into DB. | 1
Itemcost-Material |  | Create repository for Add.
Itemcost-Material |  | Create repository for Delete.
Itemcost-Material |  | Create repository for Update.
Itemcost-Material |  | Create actions in web API for Add.
Itemcost-Material |  | Create actions in web API for Delete.
Itemcost-Material |  | Create actions in web API for Update.
Itemcost-Material |  | Mapping of DataModel into Business Entity.
Itemcost-Material |  | Business service Add.
Itemcost-Material |  | Business service Delete.
Itemcost-Material |  | Business service Update.
Itemcost-Material |  | Create View. | 1
Itemcost-Material |  | Create client side and server side validation.
Itemcost-Material |  | Cosume Rest API for Add.
Itemcost-Material |  | Cosume Rest API for Update.
Itemcost-Material |  | Cosume Rest API for Delete.
|  | Total Days. | 2 |  | 0
Itemcost-Service |  | Create Table into DB. | 1
Itemcost-Service |  | Create repository for Add.
Itemcost-Service |  | Create repository for Delete.
Itemcost-Service |  | Create repository for Update.
Itemcost-Service |  | Create actions in web API for Add.
Itemcost-Service |  | Create actions in web API for Delete.
Itemcost-Service |  | Create actions in web API for Update.
Itemcost-Service |  | Mapping of DataModel into Business Entity.
Itemcost-Service |  | Business service Add.
Itemcost-Service |  | Business service Delete.
Itemcost-Service |  | Business service Update.
Itemcost-Service |  | Create View. | 1
Itemcost-Service |  | Create client side and server side validation.
Itemcost-Service |  | Cosume Rest API for Add.
Itemcost-Service |  | Cosume Rest API for Update.
Itemcost-Service |  | Cosume Rest API for Delete.
|  | Total Days. | 2 |  | 0
Itemcost-Service |  | Create Table into DB. | 1
Itemcost-Service |  | Create repository for Add.
Itemcost-Service |  | Create repository for Delete.
Itemcost-Service |  | Create repository for Update.
Itemcost-Service |  | Create actions in web API for Add.
Itemcost-Service |  | Create actions in web API for Delete.
Itemcost-Service |  | Create actions in web API for Update.
Itemcost-Service |  | Mapping of DataModel into Business Entity.
Itemcost-Service |  | Business service Add.
Itemcost-Service |  | Business service Delete.
Itemcost-Service |  | Business service Update.
Itemcost-Service |  | Create View. | 1
Itemcost-Service |  | Create client side and server side validation.
Itemcost-Service |  | Cosume Rest API for Add.
Itemcost-Service |  | Cosume Rest API for Update.
Itemcost-Service |  | Cosume Rest API for Delete.
|  | Total Days. | 2 |  | 0
Task Management | Task Creation | Create Table into DB. | 1
Task Management | Task Creation | Create repository for Add.
Task Management | Task Creation | Create repository for Delete.
Task Management | Task Creation | Create repository for Update.
Task Management | Task Creation | Create actions in web API for Add.
Task Management | Task Creation | Create actions in web API for Delete.
Task Management | Task Creation | Create actions in web API for Update.
Task Management | Task Creation | Mapping of DataModel into Business Entity.
Task Management | Task Creation | Business service Add.
Task Management | Task Creation | Business service Delete.
Task Management | Task Creation | Business service Update.
Task Management | Task Creation | Create View. | 1
Task Management | Task Creation | Create client side and server side validation.
Task Management | Task Creation | Cosume Rest API for Add.
Task Management | Task Creation | Cosume Rest API for Update.
Task Management | Task Creation | Cosume Rest API for Delete.
|  | Total Days. | 2 |  | 0
Task Management | Task Recurrence | Business logic | 1
Task Management | Task Recurrence
Task Management | Task Recurrence
Task Management | Task Recurrence
|  | Total Days. | 1 |  | 0
Task Management | Task activation | Business logic | 1
Task Management | Task activation
Task Management | Task activation
Task Management | Task activation
Task Management | Task activation
|  | Total Days. | 1 |  | 0
Task Management | NK | Business logic | 1
Task Management | NK
Task Management | NK
Task Management | NK
Task Management | NK
|  | Total Days. | 1 |  | 0
TicketManagement | Task Creation | Create Table into DB. | 1
TicketManagement | Task Creation | Create repository for Add.
TicketManagement | Task Creation | Create repository for Delete.
TicketManagement | Task Creation | Create repository for Update.
TicketManagement | Task Creation | Create actions in web API for Add.
TicketManagement | Task Creation | Create actions in web API for Delete.
TicketManagement | Task Creation | Create actions in web API for Update.
TicketManagement | Task Creation | Mapping of DataModel into Business Entity.
TicketManagement | Task Creation | Business service Add.
TicketManagement | Task Creation | Business service Delete.
TicketManagement | Task Creation | Business service Update.
TicketManagement | Task Creation | Create View. | 1
TicketManagement | Task Creation | Create client side and server side validation.
TicketManagement | Task Creation | Cosume Rest API for Add.
TicketManagement | Task Creation | Cosume Rest API for Update.
TicketManagement | Task Creation | Cosume Rest API for Delete.
|  | Total Days. | 2 |  | 0
TicketManagement | NK |  | 1
TicketManagement | NK
TicketManagement | NK
TicketManagement | NK
TicketManagement | NK
TicketManagement | NK
TicketManagement | NK
TicketManagement | NK
TicketManagement | NK
TicketManagement | NK
TicketManagement | NK
TicketManagement | NK |  | 1
TicketManagement | NK
TicketManagement | NK
TicketManagement | NK
TicketManagement | NK
|  | Total Days. | 2 |  | 0
Dashboard |  |  | 3
Dashboard
Dashboard
Dashboard
Dashboard
Dashboard
Dashboard
Dashboard
Dashboard
Dashboard
Dashboard
Dashboard |  |  | 1
Dashboard
Dashboard
Dashboard
Dashboard
|  | Total Days. | 4 |  | 0